## Detail
CSS Structure
| Create basic structure CSS for COSMO | 7
Responsive
| Create responsive layout | 14
Header
| [UI]Layout header | 1
| [UI]Integrate general API | 2
| [API]Create general infos API |  | 2
| [API]Test general infos API |  | 1
Layout
| [UI]Integrate Weather API | 2
| [UI]Make layout responsive | 2
| [UI]Get location | 1
| [API]Set google account constant |  | 0.5
Login form
| [UI]Make login form | 3
| [UI]Make directive to show warning about required fields | 2
| [UI]Integrate Login API | 2
| [UI]Make login help dialog | 2
| [UI]Test login form | 2
Change password form
| [UI]Test change password form | 3
| [UI]Make change password form | 3
| [UI]Integrate change password API | 0.5
Forcast
| [UI]Make table responsive | 1
| [UI]Make countdown directive | 1
| [UI]Integrate refresh forcast API | 0.5
| [UI]Test refresh forcast API | 2
| [API]Create API for get forcast list |  | 7
| [API]Test API for get forcast list |  | 7
Search bar
| [UI]Layout search bar | 2
| [UI]R&D search auto complete | 2
| [UI]Integrate quick search API | 1
| [UI]Test quick search API | 4
| [API]Create quick search API |  | 7
| [API]Test quick search API |  | 7
User button
| [UI]Clone change password form | 1
| [UI]Test change password form | 2
Title bar
| [UI]Layout bar for responsive | 1
| [UI]Make directive for realtime clock | 2
| [UI]Test title bar | 2
Navigation bar
| [UI]Layout navigation bar | 2
| [UI]Create router for each navigation item | 1
| [UI]Test navigation bar | 2
Show task list
| [UI]Make task list layout | 7
| [UI]Test task list | 7
| [UI]Integrate search task list API | 0.5
| [API]Create search task list API |  | 3
| [API]Test search task list API |  | 3
Add new task
| [UI]Clone layout search bar | 0.5
| [UI]Integrate search user API | 0.5
| [UI]Create add task form | 7
| [UI]Integrate role list API | 0.5
| [UI]Integrate add new task API | 1
| [UI]Test add new task | 4
| [API]Create role list API |  | 3
| [API]Create add task API |  | 3
| [API]Test role list API |  | 2
| [API]Test add task API |  | 2
Guest Search Screen
| [UI] Layout search form | 4
| [UI] Room availability chart | 3
| [UI] Integrate guest search result | 1
| [UI] Integrate room availability result when select date | 1
| [UI] Layout search result | 4
| [UI] Testing for layout search form | 7
| [API] Search guest reservation result |  | 7
| [API] Search room availability |  | 3
| [API] Total available rooms |  | 4
| [API] Sort search result |  | 3
| [UI] Testing for api search |  | 3
New Guest Reservation
| [UI] Search room & rate availability form | 2
| [UI] Integrate search room & rate availability result | 1
| [UI] Search room & rate availability chart result | 1
| [UI] 'Done' button available when Room & rate availability selected | 1
| [UI] Header bar for new guest reservation | 3
| [UI] Guest resv information bar | 2
| [UI] Guest profile form | 2
| [UI] Guest profile form validation | 2
| [UI] Integrate guest profile search | 2
| [UI] Integrate guest profile update | 2
| [UI] Testing guest profile form | 3
| [UI] Booker information form | 2
| [UI] Booker information form validation | 1
| [UI] Guest resv form | 6
| [UI] Guest resv form validation | 2
| [UI] Guest resv form testing | 1
| [UI] Room search form | 2
| [UI] Integrate room search form | 2
| [UI] Auto complete company info when key input | 2
| [UI] Update Rate Plan & Market code when update company info | 1
| [UI] Auto complete travel agent info when key input | 2
| [UI] Update Rate Plan & Market code when update travel agent info | 1
| [API] Search room & rate availability |  | 4
| [API] Format room & rate availability chart |  | 1
| [API] Guest profile search |  | 3
| [API] Guest profile update |  | 2
| [API] Guest profile validation |  | 2
| [API] Testing api guest profile |  | 2
| [API] General api for room type, market, rate plan, rate, room feature, specials, channel, guaranteed, payment, posting |  | 5
| [API] Rate plan CRUD |  | 1
| [API] Room type CRUD |  | 1
| [API] Room feature CRUD |  | 1
| [API] Market CRUD |  | 1
| [API] Channel CRUD |  | 1
| [API] Specials CRUD |  | 1
| [API] Guarantee CRUD |  | 1
| [API] Payment CRUD |  | 1
| [API] Room search |  | 3
| [UI] Integrate api save | 3
| [UI] Validation form resv | 2
| [UI] Close resv without save | 1
| [UI] Testing api create guest resv | 2
| [API] Validation form resv |  | 2
| [API] Reservation save |  | 3
| [API] Reservation confirmation number logic |  | 3
| [API] Check room type overbooked, fully booked, already booked, rate plan not available |  | 2
| [API] Testing api create guest resv |  | 2
Edit Guest Reservation
| [UI] Search resv form | 2
| [UI] Integrate search resv | 2
| [UI] Search resv result form | 2
| [UI] Sort search resv result list | 2
| [UI] Highlight record on search result | 1
| [UI] Update header bar information when change record on resv list | 1
| [UI] Integrate Check-in resv | 2
| [UI] Update invisible/visible button on header bar based on resv status | 2
| [UI] Integrate Reinstate a Cancelled/No show resv | 1
| [UI] Integrate Cancel a resv | 1
| [UI] Cancel a resv form | 2
| [UI] Integrate Cancel reason CRUD | 1
| [UI] Integrate Reverse Check-in | 1
| [UI] Integrate Reverse Checked out resv | 1
| [API] search resv |  | 3
| [API] Sort search resv result list |  | 2
| [API] Check-in resv |  | 2
| [API] Check room status (Vacant inspected/vacant dirty/oos) |  | 1
| [API] Generate Cancellation number logic |  | 1
| [API] Cancel a resv |  | 2
| [API] Reinstate a Cancelled/No show resv |  | 3
| [API] Cancel reason CRUD |  | 1
| [API] Reverse Check-in resv |  | 1
| [API] Reverse Checked out resv |  | 3
Confirmation letter
| [UI]Layout confirmation letter | 7
| [UI]Test confirmation letter | 7
| [API]Create API for load email info list |  | 2
| [API]Create export email |  | 7
| [API]Test |  | 7
Registration card
| [UI]Create dialog to print RC | 1
| [API]Support print RC by ERC |  | 7
| [API]Test print RC |  | 12
Sharer
| [UI] Sharer form | 3
| [UI] Sharer form validate | 2
| [UI] Integrate Sharer create | 2
| [UI] Testing api Sharer create | 1
| [UI] Integrate Sharer update | 2
| [UI] Testing api Sharer update | 1
| [API] Sharer form validate |  | 2
| [API] Sharer create |  | 3
| [API] Sharer update |  | 2
| [API] Testing api sharer create/update |  | 2
Sharer's Reservation
| [UI] Sharer's resv form | 3
| [UI] Sharer's resv form validate | 2
| [UI] Integrate Sharer's resv create | 2
| [UI] Testing api Sharer's resv create | 2
| [UI] Integrate Sharer's resv update | 2
| [UI] Testing api Sharer's resv update | 2
| [UI] Integrate Sharer's resv delete | 2
| [API] Sharer's resv form validate |  | 3
| [API] Sharer's resv create |  | 2
| [API] Sharer's resv update |  | 2
| [API] Testing api Sharer's resv |  | 2
| [API] Sharer's resv delete |  | 2
Room change
| [UI] Room change form | 2
| [UI] Room change form validation | 1
| [UI] Directive Room search | 2
| [UI] Integrate API Room change | 2
| [API] Room change form validation |  | 1
| [API] Room change reason |  | 1
| [API] Room change |  | 1
Transportation
[UI]Arrival Transportation form
[UI]Intergrate save arrival transportation
[UI]Intergrate update arrival transportation
[UI]Departure Transportation form
[UI]Intergrate save departure transportation
[UI]Intergrate update departure transportation
[UI]Test form arrival, departure transportation
[API]Load(search) arrival transportation
[API]Save arrival transportation
[API]Validate save arrival transportation
[API]Update arrival transportation
[API]Validate update arrival transportation
[API]Load(search) departure transportation
[API]Save departure transportation
[API]Validate save departure transportation
[API]Update departure transportation
[API]Validate update arrival transportation
[API]Test arrival, departure transportation
Notes
[UI]Notes form
[UI]Integrate save note
[UI]Integrate update note
[UI]Integrate delete note
[UI] Test U, integrate form
[API]Search note
[API]Save note
[API]Validate save note
[API]Update note
[API]Validate update note
[API]Delete note
Billing instruction
[UI]Billing Instruction form
[UI]Intergrate save billing instruction
[UI]Intergrate update billing instruction
[UI]Intergrate save extra charges
[UI]Intergrate update extra charges
[UI]Test GUI, Intergate
[API]Load(search) billing instruction
[API]Save billing instruction
[API]Update billing instruction
[API]Load(search) extra charges
[API]Save extra charges
[API]Update extra charges
[API]Test Search, Save, Edit billing instruction form
Changing log
[UI]Create stay changing Log table
[UI]Integrate changing log API
[UI]Test changing log
[UI]Use directive side bar tools
[API]Search changing log
[API]Save changing log
[API]Sent email attached changing log to multi emails
[API]Preview changing log
[API]Test api changing log
Message
| [UI]Message form | 2
| [UI]Default message form | 2
| [UI]Integrate load messge | 1
| [UI]Integrate save message | 1
| [UI]Integrate update message | 1
| [UI]Integrate delete message | 1
| [UI]Use directive side bar tools | 1
| [UI]Test form, intergrate | 1
| [UI]Integrate load default message | 1
| [API]Load(search) message |  | 1
| [API]Sent email messgae to multi emails |  | 1
| [API]Save message |  | 2
| [API]Update message |  | 1
| [API]Delete message |  | 1
| [API]Load default messages |  | 2
| [API]Test api |  | 1
Tool Bar Search
| [UI]Create toolbar search layout | 7
Profile header bar
| [UI]Layout profile header bar | 7
Search Guest Profile
| [UI]Create search Guest-profile result layout | 7
| [UI][Intergate]Search Guest-profile result | 1
| [UI]Test search Guest profile | 4
Search Travel Agent Profile
| [UI][Intergate]Search Travel Agent profile result | 1
| [UI]Customize search travel agent result layout | 2
| [UI]Test search Travel Agent profile | 4
Search Company Profile
| [UI][Intergate]Search Company-profile result | 1
| [UI]Customize search company result layout | 2
| [UI]Test search Company profile | 4
Create Guest Profile
| [UI]Create create guest profile form | 21
| [UI]Validate guest profile form | 7
| [UI][Intergate]Create Guest-profile | 1
| [UI]Test create Guest profile | 7
Create Company Profile
| [UI]Create create company profile form | 7
| [UI]Validate company profile form | 3
| [UI][Intergate]Create Company-profile | 1
| [UI]Test create Company profile | 7
Create Travel Agent Profile
| [UI]Create create travel agent profile form | 5
| [UI]Validate company profile form | 2
| [UI][Intergate]Create Company-profile | 1
| [UI]Test create Travel Agent profile | 7
Edit Guest Profile
| [UI][Intergate]Edit Guest-profile | 1
| [UI][Intergate]Delete Guest-profile | 1
| [UI]Test edit Guest Profile | 7
Edit Company Profile
| [UI][Intergate]Edit Company-profile | 1
| [UI][Intergate]Delete Company-profile | 1
| [UI]Test edit Company Profile | 7
Edit Travel Agent Profile
| [UI][Intergate]Edit Travel Agent-profile | 1
| [UI][Intergate]Delete Travel Agent-profile | 1
| [UI]Test edit Travel Agent profile | 7
Stay History
| [UI]Create stay history table | 3
| [UI]Integrate stay history API | 1
| [UI]Test stay history | 4
| [UI]Make directive side bar tools | 3
Changing Log
| [UI]Create stay changing Log table | 3
| [UI]Integrate changing log API | 1
| [UI]Test changing log | 4
Contract Rate
| [UI]Create contract rate form | 3
| [UI]Integrate Detete, Edit, New API | 2
| [UI]Test create/edit/delete contract rate form | 7
| [UI]Create contract rate list | 3
| [UI]Integrate get contract rate list API | 0.5
Guest Profile
| [API]Search with Guest-profile |  | 3
| [API]Create Guest-profile |  | 2
| [API]Validate when create Guest-profile |  | 3
| [API]Edit Guest-profile |  | 2
| [API]Validate when edit Guest-profile |  | 3
| [API]Delete Guest-profile |  | 2
| [API]Validate when delete Guest-profile |  | 3
| [API]Stay history for Guest-profile |  | 2
| [API]Changing log for Guest-profile |  | 2
| [API]Save addition phone details |  | 2
| [API]Validate addtition phone details before save |  | 3
| [API]Save addition email details |  | 2
| [API]Validate addtition email details before save |  | 2
| [API]Sent email changing logs to multi emails |  | 2
| [API]Preview changing log by PDF format |  | 2
Company Profile
| [API]Search with Company-profile |  | 3
| [API]Create Company-profile |  | 2
| [API]Validate when create Company-profile |  | 3
| [API]Edit Company-profile |  | 2
| [API]Validate when edit Company-profile |  | 3
| [API]Delete Company-profile |  | 2
| [API]Validate when delete Company-profile |  | 3
| [API]Stay history for Company-profile |  | 2
| [API]Changing log for Company-profile |  | 2
| [API]Save addition phone details |  | 2
| [API]Validate addtition phone details before save |  | 2
| [API]Save addition email details |  | 2
| [API]Validate addtition email details before save |  | 3
| [API]Sent email changing logs to multi emails |  | 2
| [API]Preview changing log by PDF format |  | 3
| [API]Search contact rate for Company-profile |  | 2
| [API]Create contact rate for Company-profile |  | 2
| [API]Edit contact rate for Company-profile |  | 2
| [API]Delete contact rate for Company-profile |  | 2
Travel Agent Profile
| [API]Search with Travel Agent-profile |  | 3
| [API]Create Travel Agent-profile |  | 2
| [API]Validate when create Travel Agent-profile |  | 3
| [API]Edit Travel Agent-profile |  | 2
| [API]Validate when edit Travel Agent-profile |  | 3
| [API]Delete Travel Agent-profile |  | 2
| [API]Validate when delete Travel Agent-profile |  | 3
| [API]Stay history for Travel Agent-profile |  | 2
| [API]Changing log for Travel Agent-profile |  | 2
| [API]Save addition phone details |  | 2
| [API]Validate addtition phone details before save |  | 2
| [API]Save addition email details |  | 2
| [API]Validate addtition email details before save |  | 3
| [API]Sent email changing logs to multi emails |  | 2
| [API]Preview changing log by PDF format |  | 3
| [API]Search contact rate for TA-profile |  | 2
| [API]Create contact rate for TA-profile |  | 2
| [API]Edit contact rate for TA-profile |  | 2
| [API]Delete contact rate for TA-profile |  | 2
Multi tenant configuration
| [API] Apply multi tenant |  | 16
User
| [API] Add new user |  | 1
| [API] Change password user |  | 1
Role
| [API] Bootstrap new role |  | 1
|  | 401.5 | 337.5
| TOTAL | 739
98.5333